Zenup Health

75-Day Flutter App Development Plan

Frontend Client · Flutter 3.x · iOS & Android

Psychiatry · Therapy · Mental Health Booking
Built for zenuphealth.com
Project Manager: Samarth Mehta
Developers: Arnav, Tarun, Yashwanth

# Table of Contents

Project Overview & Frontend Architecture	Page 3

Phase 1 — Days 1–9: Foundation & Setup	Page 4

Phase 2 — Days 10–26: Core Features & Booking Flow	Page 6

Phase 3 — Days 27–45: Advanced Telehealth & Local Persistence	Page 10

Phase 4 — Days 46–62: Polish & Testing	Page 15

Phase 5 — Days 63–75: Launch & Deploy	Page 20

Daily Deliverables Tracker	Page 23

Estimated Project Costs	Page 25

Risk Register & Launch Checklist	Page 26

# Project Overview

Zenup Health is a mental health platform offering psychiatry, therapy, and counseling booking at zenuphealth.com. This Flutter app is developed as a frontend-first client utilizing client-side state management (Riverpod), local data caching (Hive), and a  Supabase backend for user authentication and core data persistence. The architecture keeps the app fast and offline-capable, while Supabase handles secure login and syncing confirmed bookings and user profiles to the cloud.

### Project Team & Personnel

| Role | Member Name |
| --- | --- |
| Head of Engineering / PM | Samarth Mehta |
| App Developer | Arnav |
| App Developer | Tarun |
| App Developer | Yashwanth |

### Architecture Principles

Frontend-First: Full UI built and validated offline using mock repositories before backend wiring.

Local Caching: Hive database for encrypted on-device data persistence — appointments, profiles, messages.

Supabase Auth ( Backend): Supabase handles secure user sign-up, login, and session tokens only.

Supabase Data Sync: Confirmed bookings and user profiles are written to Supabase Postgres in real time.

Robust State Management: Riverpod providers cleanly separate UI from data layers.

Offline-Capable: All screens function with local Hive cache — Supabase syncs in the background.

### Complete Tech Stack

| Layer | Technology | Notes |
| --- | --- | --- |
| Frontend (App) | Flutter 3.x (Dart) | Single codebase — iOS & Android |
| Backend | Supabase (Auth + Postgres) | User login, session tokens & confirmed booking sync |
| State Mgmt | Riverpod 2.x + AsyncNotifier | Reactive, testable, mock-compatible state |
| Local Storage | Hive (Encrypted) | Encrypted offline cache & user preferences |
| Navigation | GoRouter | Declarative routing + deep links |
| Payments | Razorpay SDK (Client) | Client-side checkout integration sandbox |
| Video Call | MediaSFU SDK (Client) | Telehealth video & audio calling interface |
| Notifications | Local Notifications SDK | Scheduled check-in & app reminder alerts |
| Mocking Layer | Mock Repository Adapters | Simulated network latencies and operation buffers |
| Testing | Flutter Test + Patrol | Unit, widget, golden & integration E2E tests |

## Phase 1 — Foundation & Setup (Days 1–9)

Day 1: Project Init & Folder Architecture

Tasks:

Create Flutter project using standard naming and organization settings

Establish clean architecture directory structure (features, core, shared, mock_services)

Initialize Git repository and configure Git ignore files for sensitive environments

Add package dependencies including Riverpod, Hive local storage, and GoRouter

Configure Android and iOS project settings for minimum SDK versions

Deliverables:

Flutter project boots on emulator

Git repository initialized

Dependencies configuration complete

Day 2: Local Storage & State Management Setup

Tasks:

Configure Riverpod global state container provider wrapper

Set up application config file for environment switches (mock/dev)

Initialize Hive local storage in the main application entry point

Create a dedicated local storage service class wrapper using Hive

Verify local cache read and write flows using test key-value pairs

Deliverables:

Local storage service initialized

Riverpod state notifier configured

Cache read/write test passing

Day 3: Local Database Schema & Hive Adapters

Tasks:

Define Dart models representing User, Appointment, Mood, and Chat data structures

Register Hive type adapters and generate Hive adapters using build_runner

Create client-side data schema definitions for local models

Implement local database manager with secure AES encryption keys

Configure local data backup mechanisms and clean-up routines

Deliverables:

Hive adapters generated successfully

Local models registered

Local data security layer active

Day 4: Design System & Theme

Tasks:

Define color, typography, and spacing constants in theme config

Configure Material theme with selected typography and styling guidelines

Build reusable custom UI components: buttons, cards, inputs, badges, and avatars

Set up application asset directories for assets and icons

Add branding icons and image assets to project folders

Deliverables:

Theme configuration complete

Reusable UI widgets built

Fonts rendering correctly

Day 5: Navigation Configuration

Tasks:

Set up declarative routing using GoRouter package

Define application routing paths (splash, login, dashboard, profile, booking)

Implement navigation guard checking user client-side login state

Create bottom navigation bar layout linking main tabs

Configure deep linking pathways for application redirection

Deliverables:

All routes defined

Client-side login guard redirecting correctly

Bottom nav working

Day 6: Authentication — Supabase Auth Integration

Tasks:

Initialize Supabase Flutter SDK and configure project URL + anon key

Build login and sign-up UI with email/password validation forms

Connect login form to Supabase Auth — supabase.auth.signInWithPassword()

Connect sign-up form to Supabase Auth — supabase.auth.signUp()

Build mock Google OAuth sign-in flow for visual feedback

Handle Supabase auth error responses with user-friendly messages

Deliverables:

Supabase Auth login functional

Sign-up flow creating real user in Supabase

Auth error handling active

Day 7: Auth State & Profile Sync to Supabase

Tasks:

Listen to Supabase auth state stream and auto-route user on login/logout

On first login: show profile setup form (name, date of birth, contact)

Save completed profile to Supabase 'profiles' table via REST insert

Cache profile data locally in encrypted Hive box for offline access

Implement local file picker and upload avatar to Supabase Storage bucket

Deliverables:

Supabase auth stream auto-navigating

Profile saved to Supabase profiles table

Avatar uploaded to Supabase Storage

Day 8: Splash, Onboarding & Local State Tests

Tasks:

Build animated splash screen with entrance animations

Create multi-slide onboarding flow with local state storage

Write unit tests for authentication notifier and local storage service

Fix Phase 1 visual bugs and layout adjustments

Document environment settings and local storage structure in README

Deliverables:

Splash + onboarding working

Unit tests passing

README updated with local setup instructions

Day 9: Buffer Day — Setup & Environment Contingency

Tasks:

Resolve unexpected issues with local storage initialization or path provider

Verify Hive model migrations and key security setup on test platforms

Debug dependency conflicts or compiler issues on target platform simulators

Update local development environment onboarding documentation

Deliverables:

Verified local environment with updated configuration

Setup and storage troubleshooting notes completed

## Phase 2 — Core Features  (Days 10–26)

Day 10: Home Dashboard

Tasks:

Build Home screen with user greeting loading profile data

Create upcoming appointments widget querying local logs in Hive

Add quick-action pathways for booking, messages, and appointments overview

Create featured providers listing sorted by highest ratings

Add appointment scheduling summary widget using local sources

Deliverables:

Home screen loading cached user data

Appointments widget showing

Featured providers list complete

Day 11: Provider Discovery & Search

Tasks:

Create provider directory listing filtering by specialty

Implement client-side search functionality over provider names and bios

Design filter selection chips for medical categories

Design provider details card using profile and image resources

Implement sorting options by rating and availability slots

Deliverables:

Provider list loaded from local assets

Search and filtering functional

Sorting options active

Day 12: Provider Profile Screen

Tasks:

Fetch detailed provider profile data and reviews from local JSON assets

Display bio details, credentials, ratings, and feedback counts

Create availability calendar displaying open booking slots

Render reviews list ordered by submission date

Add booking action button redirecting to scheduling flow

Deliverables:

Provider details rendering correctly

Availability slots loaded

Reviews feed functional

Day 13: Booking Flow Steps 1 & 2

Tasks:

Implement multi-step booking state notifier using Riverpod

Step 1: Select preferred appointment medium (video, in-person, audio)

Step 2: Display date picker and fetch corresponding open slots

Create interactive time-slot grid disabling filled appointments

Store selected slot reference in scheduling state

Deliverables:

Booking state managed reactively

Date and slot selection complete

Occupied slots disabled

Day 14: Booking Flow Steps 3 & 4 — Confirm & Sync

Tasks:

Step 3: Collect billing information and pre-fill from user profile

Step 4: Display booking summary review screen

On confirm: Write appointment record to Supabase 'appointments' table

Cache confirmed appointment in local Hive box for offline access

Mark the selected slot as booked in the local calendar state

Trigger local booking success notification reminder

Deliverables:

Appointment saved to Supabase appointments table

Cached in Hive for offline

Local confirmation alert triggered

Day 15: Appointments Management Screen

Tasks:

Create appointments interface with tabs for upcoming, past, and cancelled

Connect dashboard with local appointments stream listener for live status updates

Implement reschedule option updating local booking slot and status

Implement cancel option updating booking status in local storage

Add cancellation policy modal warning users before confirmation

Deliverables:

Appointments list updating in real time

Reschedule request processing

Cancellation flow active

Day 16: Client-Side Payment Gateway Integration

Tasks:

Configure Razorpay SDK package for client checkout flow

Initialize client payment parameters and trigger checkout request from Flutter

Design mock payment checkout screen with secure Razorpay branding

Handle payment checkout success, failure, and cancellation states in UI

Update local appointment record with transaction ID and status

Deliverables:

Razorpay SDK client integrated

Mock checkout screen functional

Payment status saved in local database

Day 17: Billing & Invoices UI

Tasks:

Manage member insurance detail fields within user profile form

Retrieve paid appointments list to render billing history

Implement client-side PDF document generator in Flutter

Generate invoice and receipt PDFs directly on the device

Add insurance information edit form with form validation rules

Deliverables:

Insurance fields editable in profile

Billing history populated

Client-side PDF invoice generation functional

Day 18: Client-Side Messaging UI

Tasks:

Build chat interface between patient and provider

Load historical message records from local Hive store

Implement send message operation saving new message to Hive

Simulate chat stream with automated responses for demo purposes

Configure typing indicators using local timer triggers

Deliverables:

Message history loading from Hive

Message sending operational

Typing indicators simulated

Day 19: Local Scheduled Notifications

Tasks:

Configure local notification scheduler package

Schedule automated reminder triggers for upcoming appointments

Set up daily check-in prompt notifications at custom times

Register local notification channels for Android and iOS

Set up deep links to open corresponding screens when tapping notification

Deliverables:

Local scheduler configured

Automated reminders working

Notification deep links active

Day 20: Buffer Day — Payment SDK Sandbox & Theme Calibration

Tasks:

Troubleshoot Razorpay SDK integration or layout anomalies

Test simulated slow state changes and loading spinners during checkout

Adjust app color palette and dark/light theme consistency

Verify local state persistence after cold restarts

Deliverables:

Razorpay sandbox flow verified

Layout theme audits completed

Day 21: Multi-Provider Schedule Sync

Tasks:

Design Dart data structures representing multi-provider slots and schedule sync

Create local database model for tracking schedule changes and updates

Implement logic to prevent double-booking on overlapping provider slots

Deliverables:

Provider sync models initialized

Schedule overlap resolver class created

Day 22: Booking Customization UI

Tasks:

Build custom notes field during booking to add patient concerns

Implement selector for language preference or doctor gender flags

Design validation rules for booking custom fields

Deliverables:

Booking concerns field functional

Custom doctor flags verified

Day 23: UI Concurrency Guards & Input Validation

Tasks:

Implement client-side transaction locks to prevent double-booking on quick double-taps

Design input guard validation rules for all interactive forms

Write widget tests simulating rapid simultaneous user inputs on calendar slots

Deliverables:

Client-side booking locking logic operational

Double-tap form validations active

Day 24: In-App Booking Cancellation & Client Refund Simulation

Tasks:

Build slot release animation on booking cancellation

Simulate wallet credits refund on cancellations within policy limits

Set up local notifications alerting user of slot release

Deliverables:

Local refund/credit simulation active

Slot release state updated in Hive

Day 25: Client-Side State Stress Testing

Tasks:

Perform memory stress testing with large local datasets (1000+ mock slots)

Verify UI rendering frame rates and scroll performance

Optimize local search index queries over provider profiles

Deliverables:

Stress testing completed

Local search index latency minimized

Day 26: Local PDF Invoice Export

Tasks:

Automate local patient invoice PDF generation post-booking

Map billing details and invoice download paths to local appointment histories

Build manual invoice download button in patient's billing screen

Deliverables:

Invoice PDF export functional

Billing history download link verified

## Phase 3 — Advanced Features & Local Caching (Days 27–45)

Day 27: Telehealth Video UI (MediaSFU Integration)

Tasks:

Add video consultation SDK module to the application dependencies

Configure video calling client connection details for audio and video rooms

Build telehealth call screen displaying remote and local camera streams

Add interface controllers for camera toggling, mic mute, and screen sharing

Store mock session credentials securely within local appointment notes

Deliverables:

Telehealth video call working on emulator

Connected to media room layout

Telehealth call controls functional

Day 28: Telehealth — Device Testing & Polish

Tasks:

Test telehealth call screen on physical iOS and Android hardware

Add network connection quality indicators and status overlay to call screen

Build in-app post-session feedback survey

Manage application backgrounding states (Picture-in-Picture mode) during live calls

Integrate interactive chat panel overlay into the active video session

Deliverables:

Video UI tested on real devices

Post-session survey interface complete

In-call chat overlay working

Day 29: Prescription Tracking

Tasks:

Create prescriptions screen showing active user prescriptions

Display detail card for medication names, dosages, schedules, and providers

Implement refill request flow with mock request notifications in app

Configure local system notifications to remind users to take medication

Build listing filter displaying archived or inactive prescriptions

Deliverables:

Prescriptions list rendering

Refill request flow functional

Local medication reminders

Day 30: Health Records File Explorer

Tasks:

Build personal health records file explorer interface

Implement local file picker to select health documents

Encrypt documents before saving to secure local application directory

Retrieve listing of files registered under the user's local directory

Generate secure file preview screen inside the application

Deliverables:

Local health records explorer complete

Files encrypted and stored

In-app file preview working

Day 31: Advanced Booking Filters

Tasks:

Build search filter form allowing sorting of doctor directory by availability timeslots

Create active filters status bar widget for selected criteria

Build interactive filters resetting animation

Implement favorites list caching doctors using Hive database box

Generate provider rating summaries calculating score stats locally

Deliverables:

Favorites system registered in Hive

Availability filters functional

Dynamic search active

Day 32: In-App Alerts & Settings

Tasks:

Build list showing local notifications and system alerts

Create account settings screen allowing users to edit profile and reset password

Configure notification preference switches and save choices in local profile

Integrate option for analytics collection opt-out in settings

Add local data purging tool triggering secure storage cleanup

Deliverables:

Notifications center screen active

Settings updating preferences in Hive

Data purging flow functional

Day 33: Provider Rating Form

Tasks:

Build rating feedback form linking patient and provider

Configure validation to only allow feedback for completed appointments

Recalculate average provider rating locally when new feedback is submitted

Update provider local cache database in Hive

Display updated review feed on the provider details screen

Deliverables:

Review form UI complete

Provider rating auto-calculated locally

Reviews visible on details profile

Day 34: Local Appointment Alerts & Campaign Prompts

Tasks:

Create scheduled timer checking for upcoming 24-hour bookings

Trigger local notification alert for upcoming patient slots

Implement in-app campaign banner prompts suggesting scheduling

Verify user notification preferences before showing campaign banners

Deliverables:

Timer check active

24-hour alerts functional

Campaign prompts working

Day 35: Medication Reminder Alerts & Logs

Tasks:

Build scheduled timers for medication schedule intakes

Create localized daily logs tracking consumed doses

Verify medication alerts triggers using background task scheduler

Deliverables:

Medication reminders working

Push alarms configured

Intake logs saved locally

Day 36: Telehealth Connection Diagnostics UI

Tasks:

Design call diagnostic overlay alerting user of network issues

Log call exception events in local diagnostic logs

Set up automatic rescheduling recommendation dialogs for patients

Deliverables:

Diagnostics overlay functional

Call failure logging active

Reschedule dialog active

Day 37: Post-Call Consultation Summary & Review

Tasks:

Trigger post-consultation feedback prompt on call end

Sync review score and comments to local appointment history

Design escalation dialog for negative rating feedback

Deliverables:

Post-call prompt active

Reviews logged in local history

Escalation dialog verified

Day 38: Offline Outbox Queue & Sync

Tasks:

Implement offline sync manager caching user actions while offline

Display connectivity banner when app is offline

Implement retry logic to process outbox on reconnect

Clear outbox queue database on logout

Deliverables:

Outbox queue active

Offline banner working

Cache cleared on logout

Day 39: Referral Sharing UI

Tasks:

Add referral code generation logic based on user profile metadata

Generate unique alphanumeric code for each user on sign-up

Enable referral code sharing via native share utility (share_plus)

Apply registration attribution logic to credit referred users

Create rewards display showing total counts of successful referrals

Deliverables:

Referral code generated

Native share sheet working

Rewards dashboard complete

Day 40: Accessibility & Localization

Tasks:

Audit application layout against accessibility standard checklists

Add semantic labels and accessibility tags to all interactive components

Configure localization libraries for multi-language display support

Create translated text resource files for supported languages

Test application interface using system screen reader tools

Deliverables:

Accessibility audit complete

Screen reader working

Spanish translations added

Day 41: Security Hardening & Encryption

Tasks:

Verify that all local database boxes in Hive use AES-256 encryption keys

Implement local biometric authentication check (fingerprint/face)

Encrypt local file directories containing personal health documents

Add secure SSL pinning configuration for external API calls

Audit local security parameters in build configurations

Deliverables:

Local database encrypted

Biometric auth gate working

Folder encryption active

Day 42: Phase 3 Integration Test & Demo

Tasks:

Run full client scenario flow testing all advanced features

Profile memory performance and resolve any identified leaks

Review local query execution latency and optimize list indexing

Conduct system walkthrough demo highlighting completed functionality

Deliverables:

Integration tests passing

No memory leaks

Walkthrough demo verified

Day 43: Buffer Day — Telehealth Call Screens & Layout Adjustments

Tasks:

Debug device hardware permission flows (mic/camera) on physical target platforms

Verify offline storage caching and outbox sync queue on flaky networks

Resolve layout responsiveness issues for telehealth overlay screens on tablets

Deliverables:

Offline outbox verified

Telehealth call overlays tested on tablet layouts

Day 44: Local Cache Pruning & Purging Utility

Tasks:

Implement memory cleanup routines deleting expired schedules and logs

Create diagnostic dashboard showing cache size

Verify that GDPR-compliant profile and appointment purge flows delete completely

Deliverables:

Local cache statistics operational

Data cache purging utility active

GDPR deletion verified

Day 45: Offline Flow Simulation Dry-Run

Tasks:

Simulate extended offline session with multi-booking and messaging flows

Audit local outbox queue storage limits and retry counts

Conduct offline-to-online reconciliation dry-run test

Deliverables:

Offline flow simulations complete

Offline sync outbox validated

Reconciliation logic verified

## Phase 4 — Polish & Testing (Days 46–62)

Day 46: UI Animation Polish

Tasks:

Hero transitions between provider list and provider profile screens

Shimmer loading placeholders on all list screens during data fetch

Lottie animations for empty states (no appointments, no messages)

Micro-interactions: button press haptic feedback, card tap scale

Smooth PageView transitions in onboarding flows

Deliverables:

Hero transitions working

Shimmer on all loaders active

Lottie empty states rendering

Day 47: Error Handling & Empty States

Tasks:

Wrap all repository calls in try/catch blocks with custom exceptions

Show user-friendly, localized error messages in UI

Empty state layouts for: no appointments, no messages, no prescriptions

Full-screen error widget with retry button that re-calls service notifier

Network connectivity lost banner via connectivity_plus package

Deliverables:

Friendly error screens active

Empty states on all screens

Retry widget functional

Day 48: Performance Optimization

Tasks:

Profile all screens with Flutter DevTools to ensure 60fps

Add const constructors to static layouts and components

Optimize local list builders with lazy loading and pagination

Lazy load cached images using cached_network_image package

Reduce widget rebuilds by isolating Riverpod state select parameters

Deliverables:

60fps on all screens

Paginated list builders active

Images cached locally

Day 49: Unit Testing — Mock Repositories

Tasks:

Mock repository interfaces using mocktail package

Test MockAppointmentRepository: fetch, insert, update, cancel

Test AuthNotifier: sign in, sign up, sign out state transitions

Test MockProfileRepository: fetch profile, update profile

Test BookingNotifier state machine (step 1 to 4 confirm flows)

Deliverables:

Repository tests passing

AuthNotifier tests passing

80%+ business logic coverage

Day 50: Widget & Golden Testing

Tasks:

Write widget tests for custom design widgets (ZButton, ZCard, ZInput)

Test booking flow screens using mocked Riverpod providers

Test login form validations (empty, invalid email, short password)

Perform golden tests for visual layout regression monitoring

Test provider profile card rendering with mock datasets

Deliverables:

Widget tests complete

Golden tests passing

Validation tests active

Day 51: Patrol E2E Testing

Tasks:

Write Patrol E2E test journey: signup, complete profile, book, pay

Write Patrol E2E test: login, view bookings, cancel booking

Run Patrol integration tests on physical iOS and Android devices

Add E2E tests to GitHub Actions CI workflow runs

Deliverables:

3 E2E test journeys passing

Real device tests completed

CI running Patrol

Day 52: Internal Beta Distribution

Tasks:

Build release IPAs (iOS) and App Bundles (AAB for Android)

Upload to TestFlight and invite internal team (10 testers)

Upload to Google Play Console Internal Testing track

Configure Sentry SDK client-side crash reporting in main

Collect structured feedback from internal team using form

Deliverables:

TestFlight build live

Play Console internal track live

Feedback form distributed

Day 53: App Assets Preparation & Optimization

Tasks:

Audit app assets bundle size to minimize final application payload

Optimize all PNG/JPEG/Lottie assets using compression tools

Compress font files and remove unused font variations

Clean up unused package dependencies in pubspec.yaml

Deliverables:

Assets optimized

Package bundle size minimized

Cleaner build output ready

Day 54: External Beta — 50 Users

Tasks:

Expand TestFlight invite list to 50 external beta testers

Expand Play Console closed track to 50 external beta testers

Monitor Sentry crash logs for uncaught client exceptions

Triage and resolve high-priority beta user bug reports

Test performance on older physical target devices

Deliverables:

50 external testers active

Sentry telemetry monitored

Beta crash reports resolved

Day 55: Local PHI Scrubbing & Log Security

Tasks:

Audit application logs to ensure no protected health info is outputted

Configure local log rotation and diagnostic log file size limits

Verify secure key storage configurations in Vault/Keyring platforms

Deliverables:

PHI data scrubbing active

Local log security verified

Encrypted log export ready

Day 56: Offline Outbox Queue & API Webhook Failover

Tasks:

Build offline sync manager for outbox sync queue

Write local db logic monitoring retry limits and sync statuses

Verify failover handling under simulated network outages

Deliverables:

Outbox sync queue verified

API failure logs active

Failover scenarios tested

Day 57: Hive Database Integrity Auditing

Tasks:

Perform database integrity checks on local Hive files during boot

Audit local cache synchronization logs for structural discrepancies

Design auto-repair logic resolving corrupted local cache files

Deliverables:

Hive integrity check active

Cache database check completed

Auto-repair routines verified

Day 58: Buffer Day — Beta Bug Triaging & Crash Fixes

Tasks:

Review Sentry crash reports from active TestFlight and Play Console closed track

Triage and fix critical visual bugs or state exceptions in booking flow

Hotfix high-impact exception triggers in authentication and calendar widgets

Build and deploy update builds to Apple TestFlight and Google Play Console

Deliverables:

All reported blocking exceptions resolved

Updated beta builds successfully deployed

Day 59: Buffer Day — Local Security Verification

Tasks:

Verify that all local database files use secure encryption keys

Confirm that no patient information is outputted to device console logs

Verify the end-to-end data export and delete GDPR flows

Review App Store and Google Play data safety declaration questionnaires

Deliverables:

Security configuration verified

Local logs audited and locked

Data safety checklists ready

Day 60: Compliance & Privacy Review

Tasks:

Ensure all local database encryption is verified

Ensure no PHI is outputted to client-side logs or crash logs

Add in-app privacy policy and terms of service screens

Implement client-side GDPR data export utility

Implement client-side GDPR data deletion utility

Deliverables:

Encryption verified

Privacy policy screens in app

GDPR data flows functional

Day 61: Bug Fix Sprint

Tasks:

Triage all user feedback and bug reports from external beta

Fix all crash exceptions on older devices

UI fixes for small screen layout responsiveness

Fix local notification scheduler triggers

Upload final release candidate build to store consoles

Deliverables:

All crashes fixed

UI layout bugs resolved

Final release build ready

Day 62: Release Candidate & Sign-Off

Tasks:

Full regression testing of all frontend client flows

Tag release candidate in Git repository: v1.0.0-rc1

Stakeholder sign-off meeting

Freeze features - no new features until v1.1

Prepare App Store and Google Play metadata, screenshots, and descriptions

Deliverables:

Release candidate tagged

Stakeholder sign-off complete

Store metadata ready

## Phase 5 — Launch & Deploy (Days 63–75)

Day 63: App Store Assets & Metadata

Tasks:

Design screenshots for all required sizes (6.7", 6.1", 5.5", iPad)

Write App Store description with mental health and therapy keywords

Create 30-second app preview demonstration video

Finalize 1024x1024px App Store icon

Live privacy policy and terms of service URLs on website

Deliverables:

Screenshots ready

App Store metadata copy finalized

Privacy link live

Day 64: iOS App Store Submission

Tasks:

Configure Xcode signing and distribution credentials

Build release IPA using command: flutter build ipa --release

Upload IPA to App Store Connect using Fastlane tools

Complete App Store Connect review questionnaires (encryption, data safety)

Submit for Apple review

Deliverables:

IPA uploaded to App Store Connect

Connect questionnaires complete

Submitted to Apple for review

Day 65: Google Play Submission

Tasks:

Build Android App Bundle: flutter build appbundle --release

Sign with release keystore credentials

Upload App Bundle (AAB) to Google Play Console Production track

Complete Google Play Store listing information

Publish build for Google Play review

Deliverables:

AAB uploaded to Play Console

Play Store listing complete

Live on Google Play

Day 66: Review Delay Buffer — App Store Feedbacks

Tasks:

Monitor App Store Connect review progress and respond immediately to reviewer inquiries

Address potential app classification queries regarding medical category

Prepare alternative metadata descriptions if requested by reviewers

Configure pricing tiers and test-user credentials in App Store Connect

Deliverables:

Apple reviewer feedback handled

iOS store requirements met

Day 67: Review Delay Buffer — Google Play Console Closed Testing

Tasks:

Verify that closed-testing compliance tracks remain active with required testers

Monitor Google Play dashboard for console alerts or review delays

Review pre-launch reports generated by the Play Console test lab

Prepare fallback builds in case of build-rejection notifications

Deliverables:

Google pre-launch alerts resolved

Android store requirements met

Day 68: Sentry & Mixpanel Setup

Tasks:

Enable Sentry crash reporting configuration in the production app

Configure Sentry alerts for new crash types and anomalies

Set up Mixpanel events: app_open, booking_started, payment_success

Create Mixpanel funnel: Provider View to Book to Pay to Confirm

Deliverables:

Sentry alerts configured

Mixpanel funnels active

Production monitoring live

Day 69: App Store Optimization & Marketing

Tasks:

Research top search keywords for mental health apps

Optimize App Store title and subtitle with target keywords

Set up Apple Search Ads campaign

Set up Google UAC campaign for Android installs

Announce launch on LinkedIn, Instagram, and health tech communities

Deliverables:

Listings optimized

Marketing campaigns active

Launch announced

Day 70: Launch Day Monitoring

Tasks:

Monitor Sentry dashboard for any crash reports from production users

Watch for new reviews on App Store and Google Play Console

Monitor booking conversion rates in Mixpanel funnels

Triage and prepare hotfixes if any P0 crashes occur

Deliverables:

Launch stable

Sentry monitored

Conversion rates tracked

Day 71: Post-Launch Data Analysis

Tasks:

Analyze first 7 days: installs, DAU, booking conversion, drop-offs

Query local Hive stats database to find popular provider categories

Identify top 3 friction points in user experience funnels

Survey first 50 active users for qualitative feedback

Document findings in v1.1 planning documentation

Deliverables:

User behavior report written

Top friction points identified

v1.1 planning doc started

Day 72: Retrospective & v1.1 Roadmap

Tasks:

Full project retrospective with team (what went well, what to improve)

Publish v1.1 public roadmap overview

Set 90-day OKRs: target bookings, DAU, retention rates

Start v1.1 backlog: telehealth group sessions, Apple Health integration

Celebrate launch - 75 days complete!

Deliverables:

Retrospective complete

v1.1 roadmap published

OKRs set for next quarter

Day 73: Post-Launch Buffer — Performance Tuning

Tasks:

Monitor application frame rates and page rendering performance on older devices

Analyze Sentry transaction metrics to find slow rendering states

Verify Sentry/Mixpanel analytics webhook performance in production

Deliverables:

Telemetry analyzed

Performance tuning complete

Day 74: Post-Launch Buffer — Production Feedback

Tasks:

Monitor customer support channels for login or booking layout complaints

Draft and verify hotfixes for production styling bugs or local storage issues

Update App Store and Google Play Console support resources and links

Deliverables:

Initial user issues triaged

Minor updates rolled out

Day 75: Buffer Day — Handoff & Backlog Grooming

Tasks:

Conduct a final engineering retrospective and update code documentation in the repository

Clean up development and staging local configuration settings

Prioritize features in the backlog for the upcoming v1.1 version cycle

Prepare system administration handover documentation for the client team

Deliverables:

Engineering retro summary written

Roadmap backlog prioritized

Handover documentation ready

# Daily Deliverables Tracker

Check off each day as it is completed.

| Day | Ph | Deliverable Description | Done |
| --- | --- | --- | --- |
| 1 | 1 | Flutter project boots on emulator | [ ] |
| 2 | 1 | Local storage service initialized | [ ] |
| 3 | 1 | Hive adapters generated successfully | [ ] |
| 4 | 1 | Theme configuration complete | [ ] |
| 5 | 1 | All routes defined | [ ] |
| 6 | 1 | Supabase Auth login functional | [ ] |
| 7 | 1 | Supabase auth stream auto-navigating | [ ] |
| 8 | 1 | Splash + onboarding working | [ ] |
| 9 | 1 | Verified local environment with updated configuration | [ ] |
| 10 | 2 | Home screen loading cached user data | [ ] |
| 11 | 2 | Provider list loaded from local assets | [ ] |
| 12 | 2 | Provider details rendering correctly | [ ] |
| 13 | 2 | Booking state managed reactively | [ ] |
| 14 | 2 | Appointment saved to Supabase appointments table | [ ] |
| 15 | 2 | Appointments list updating in real time | [ ] |
| 16 | 2 | Razorpay SDK client integrated | [ ] |
| 17 | 2 | Insurance fields editable in profile | [ ] |
| 18 | 2 | Message history loading from Hive | [ ] |
| 19 | 2 | Local scheduler configured | [ ] |
| 20 | 2 | Razorpay sandbox flow verified | [ ] |
| 21 | 2 | Provider sync models initialized | [ ] |
| 22 | 2 | Booking concerns field functional | [ ] |
| 23 | 2 | Client-side booking locking logic operational | [ ] |
| 24 | 2 | Local refund/credit simulation active | [ ] |
| 25 | 2 | Stress testing completed | [ ] |
| 26 | 2 | Invoice PDF export functional | [ ] |
| 27 | 3 | Telehealth video call working on emulator | [ ] |
| 28 | 3 | Video UI tested on real devices | [ ] |
| 29 | 3 | Prescriptions list rendering | [ ] |
| 30 | 3 | Local health records explorer complete | [ ] |
| 31 | 3 | Favorites system registered in Hive | [ ] |
| 32 | 3 | Notifications center screen active | [ ] |
| 33 | 3 | Review form UI complete | [ ] |
| 34 | 3 | Timer check active | [ ] |
| 35 | 3 | Medication reminders working | [ ] |
| 36 | 3 | Diagnostics overlay functional | [ ] |
| 37 | 3 | Post-call prompt active | [ ] |
| 38 | 3 | Outbox queue active | [ ] |
| 39 | 3 | Referral code generated | [ ] |
| 40 | 3 | Accessibility audit complete | [ ] |
| 41 | 3 | Local database encrypted | [ ] |
| 42 | 3 | Integration tests passing | [ ] |
| 43 | 3 | Offline outbox verified | [ ] |
| 44 | 3 | Local cache statistics operational | [ ] |
| 45 | 3 | Offline flow simulations complete | [ ] |
| 46 | 4 | Hero transitions working | [ ] |
| 47 | 4 | Friendly error screens active | [ ] |
| 48 | 4 | 60fps on all screens | [ ] |
| 49 | 4 | Repository tests passing | [ ] |
| 50 | 4 | Widget tests complete | [ ] |
| 51 | 4 | 3 E2E test journeys passing | [ ] |
| 52 | 4 | TestFlight build live | [ ] |
| 53 | 4 | Assets optimized | [ ] |
| 54 | 4 | 50 external testers active | [ ] |
| 55 | 4 | PHI data scrubbing active | [ ] |
| 56 | 4 | Outbox sync queue verified | [ ] |
| 57 | 4 | Hive integrity check active | [ ] |
| 58 | 4 | All reported blocking exceptions resolved | [ ] |
| 59 | 4 | Security configuration verified | [ ] |
| 60 | 4 | Encryption verified | [ ] |
| 61 | 4 | All crashes fixed | [ ] |
| 62 | 4 | Release candidate tagged | [ ] |
| 63 | 5 | Screenshots ready | [ ] |
| 64 | 5 | IPA uploaded to App Store Connect | [ ] |
| 65 | 5 | AAB uploaded to Play Console | [ ] |
| 66 | 5 | Apple reviewer feedback handled | [ ] |
| 67 | 5 | Google pre-launch alerts resolved | [ ] |
| 68 | 5 | Sentry alerts configured | [ ] |
| 69 | 5 | Listings optimized | [ ] |
| 70 | 5 | Launch stable | [ ] |
| 71 | 5 | User behavior report written | [ ] |
| 72 | 5 | Retrospective complete | [ ] |
| 73 | 5 | Telemetry analyzed | [ ] |
| 74 | 5 | Initial user issues triaged | [ ] |
| 75 | 5 | Engineering retro summary written | [ ] |

# Estimated Project Costs

Direct monetary costs required to publish, deploy, host, and maintain the Zenup Health mobile application.

| Item / Service | Billing Frequency | Estimated Cost | Purpose / Notes |
| --- | --- | --- | --- |
| Google Play Console | One-time | $25 USD | Required developer account for Android publishing. |
| Apple Developer Program | Annual | $99 USD / year | Required developer account for iOS publishing. |
| MediaSFU Meetings | Monthly (Usage) | $162 USD / month | Client video calling sessions usage (10% discount). |
| Razorpay Gateway | Transaction-based | 2.0% per transaction (+ GST) | Domestic payment processing fee for client transactions. |
| Sentry Error Tracker | Free Tier | $0 USD | Client-side crash and error tracking. |

# Risk Register

| Risk | Level | Cause | Mitigation |
| --- | --- | --- | --- |
| Apple Review Rejection | High | Missing privacy declarations for health data | Add NSHealthShareUsageDescription, privacy policy URL, and data use disclosures before Day 43 |
| Local PHI Storage Security | High | Local patient data stored insecurely on device | Encrypt Hive database boxes using keys stored in keychain/keystore using secure storage |
| Razorpay SDK Timeout | Medium | Client-side payment gateway fails to connect or times out | Implement robust state retry mechanisms and check connectivity state dynamically |
| MediaSFU Room Expiry | Medium | Call drops if session credentials expire | Implement client-side token refresh and auto-reconnect flow in video controller |
| In-App Performance | Medium | High memory usage from video/charts leads to app crashes on older hardware | Profile memory with DevTools, dispose controllers, and paginate local list builders |

# Launch Checklist

### App Store (iOS)

[  ] App icon 1024x1024px — no alpha, no rounded corners (Apple adds them)

[  ] Screenshots for 6.7", 6.1", 5.5", 12.9" iPad

[  ] Age rating 17+ selected (health / medical content)

[  ] Privacy policy and terms of service URLs in App Store Connect

[  ] NSHealthShareUsageDescription in Info.plist if using HealthKit

[  ] Apple Sign-In implemented (required when any other OAuth is present)

[  ] TestFlight tested with 50+ users before production submission

### Google Play (Android)

[  ] Feature graphic 1024x500px

[  ] Screenshots for phone and 7" + 10" tablet

[  ] Content rating questionnaire complete (Health category)

[  ] Target SDK 34+ (Android 14 requirement)

[  ] App Bundle (AAB) uploaded — NOT APK

[  ] Data safety section filled (data collected, shared, encrypted)

[  ] Closed testing with 20+ testers before production

### Flutter App Hardening

[  ] ProGuard rules configured for Android release build

[  ] iOS bitcode disabled (deprecated — ensure Xcode setting correct)

[  ] Client API keys stored securely in native config or env files

[  ] Certificate pinning implemented for MediaSFU and Razorpay API calls

[  ] Biometric auth gate on sensitive screens

[  ] Sentry or Crashlytics configured for production crash tracking

[  ] App version and build number incremented (pubspec.yaml)